## Phase3-TeamPlanning2023
CSI4142 - Project 2023
Phase 4 - Data Mining
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Data preprocessing
Data summarisation | Lauren Gu | 2024-04-02 | 2024-04-03 | 1 | 1
.. Visualisation of attributes | Lauren Gu | 2024-04-02 | 2024-04-03 | 1 | 0.5
Data transformation | Lauren Gu and Angus Leung | 2024-04-02 | 2024-04-03 | 1 | 1
.. Missing values | N/A | Done in phase 2 | Done in phase 2 | 0 | 0
.. Categorical data | Lauren Gu and Angus Leung | 2024-04-02 |  | 0.25 | 0.25
.. Numeric data | Lauren Gu and Angus Leung | 2024-04-02 |  | 0.25 | 0.25
.. Feature selection | Lauren Gu and Angus Leung | 2024-04-02 |  | 0.25 | 0.25
Data mining - Classification
Decision tree | Lauren Gu | 2024-04-05 | 2024-04-08 | 1 | 0.5
Gradient Boosting | Lauren Gu | 2024-04-05 | 2024-04-09 | 1 | 0.5
Random Forests | Angus Leung | 2024-04-05 | 2024-04-08 | 1 | 0.5
Comparison of results | Lauren Gu and Angus Leung | 2024-04-05 | 2024-04-09 | 1 | 1
Summary | Lauren Gu and Angus Leung | 2024-04-05 | 2024-04-09 | 1 | 1
Anomaly detection
One-class SVM | Lauren Gu | 2024-04-05 | 2024-04-09 | 1 | 1
Summary | Lauren Gu | 2024-04-05 | 2024-04-09 | 0.5 | 0.5
Other tasks - please specify