## Sheet1
CSI4142 - Project W23
Phase 2- Physical design and data staging
Teamwork - breakdown of duties
Group 31: Lauren Gu, Angus Leung, Ali Bora Nurgoren
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Create database instance | Angus Leung | 2024-03-15 | 2024-03-19 | 3 | 3
Create date dimension | Angus Leung | 2024-03-15 | 2024-03-19
Create dealership dimension | Angus Leung | 2024-03-15 | 2024-03-19
Create customer dimension | Angus Leung | 2024-03-15 | 2024-03-19
Create car_sales dimension | Angus Leung | 2024-03-15 | 2024-03-19
Create car dimension | Angus Leung | 2024-03-15 | 2024-03-19
Staging date dimension | Angus Leung and Lauren Gu | 2024-03-17 | 2024-03-27
Staging dealership dimension | Angus Leung and Lauren Gu | 2024-03-17 | 2024-03-27 | 4 | 5 | Had to redo a some queries. Issues handling foreign keys when inserting data into fact table.
Staging customer dimension | Angus Leung and Lauren Gu | 2024-03-17 | 2024-03-27
Staging car_sales fact table | Angus Leung and Lauren Gu | 2024-03-17 | 2024-03-27
Staging cardimension | Angus Leung and Lauren Gu | 2024-03-17 | 2024-03-27
Surrogate key pipeline | Angus Leung | 2024-03-15 | 2024-03-19 | 1 | 1
Data quality handling and reporting | Angus Leung and Lauren Gu | 2024-03-10 | 2024-03-10 | 2 | 4 | Unexepected challenges when joining features and sales datasets.
Write report including high level schematic | Angus Leung and Lauren Gu | 2024-03-20 | 2024-03-27 | 2 | 2